## Read Me
Tab | Content
Roadmap | High level project tasks with deadlines
About the Team | Introduction to the team members
Leave tracker | Track who is on leave

## Roadmap
Sprint Planning
Week | Event
2025-03-30 | Phase 1: Planning
2025-04-06 | POC + Phase 1 sync
2025-04-13 | POC + Phase 2: Building
2025-04-20 | Phase 2: Building
2025-04-27 | Phase 2: Building | Berkeley Midpoint check
2025-05-04 | Phase 3: Iterate
2025-05-11 | Phase 3: Iterate
2025-05-18 | Phase 4: Report
2025-05-25 | Submission
Phase 1 |  |  | MVP
Draft & Sync on objectives |  |  | Build an environment where agents interact
Define final output |  |  | Agents can make 1 action a day, but can send 5 messages to each other a day.
Proposal on what to build |  |  | Print state of environment and agents at every event
Propose resources and constraints and objectives
Propose simulation design and data collection
Propose & sync on logistics - github? collab? llm responses & state data storage?
Phase 2
Build core simulation environment
Build agents
Integrate agents and trial runs
Milestone: Full run with data collected
Phase 3
Iterate and document all changes and reason behind it

## About the Team
Fun facts about the team [we can pull this into the final presentation]
Name | Preferred Name | About me | Timezone | Project Available Times | IST (GMT +5.30) | Communication Preferences | LinkedIn | Fun Fact!
Yash Yeola |  | Experience: I work as a data scientist at a consultancy. Worked on a couple of GenAI projects at my company using Gemini Niche: Explainable ML (Symbolic Regression, LLMs for explanations, etc.) | BST (GMT+1) | Weekdays: 17:00-21:00 Weekends: 07:00-21:00 (Contactable during these times) | Weekdays: 21:30 - 01:30 (next day) Weekends: 11:30 - 01:30 (next day) | Slack, Whatsapp, I can probably get around Discord | https://www.linkedin.com/in/yash-yeola/ | I play the guitar and tabla
Gabriel Zhou | Gabriel | AI Lab in a Bank in Singapore leading NLP development for 8 years, moved to a Silicon Valley healthtech startup where I lead the growth team. | PST (GMT -8) | Weekdays: 09:00-16:00, 22:00-01:00 Weekends: 22:00-01:00 | Weekdays: 11:30 - 14:30, 22:30 - 05:30 (next day) Weekends: 11:30 (next day) - 14:30 (next day) | Slack, Whatsapp, I can probably get around Discord | https://www.linkedin.com/in/gabriel-zhou/ | As an artillery commander I rained hell upon LOTR Mt Doom in NZ
Debjyoti Ray(Dev) | Dev | Experience: I work as an AI engineer at Alma. Previously worked as a research intern in Univ. of Missouri-Columbia in GraphRAG; and currently deeply interested in LLMs, RL in LLMs and the agentic space. | IST (GMT+5:30) | Weekdays(19:00-22:00, 2:30-4:30); weekends(13:00-22:00) Monday: 11:30-18:30 Tuesday: 14:30-18:30 Wednesday:16:30-18:30 Thursday: 16:30-18:30 | weekdays: 19:00 - 22:00, 2:30 - 4:30 (next day); weekends: 13:00 - 22:00 | Slack, Whatsapp, I can probably get around Discord | https://www.linkedin.com/in/debjyoti5811/ | subtle explorer
Satyam Keshri | Satyam | Experience: Working as an AI Engineer at ULS. Focused on AI safety and compliance Worked on few projects for RAG based applications/agents and QnA chatbot. | IST (GMT+5:30) |  |  | Whatsapp, Discord | https://www.linkedin.com/in/satyamk19 | I am the unofficial tour plannar of my friends group
Jekaterina Novikova | Jekaterina | AI/NLP researcher, 10 years of postdoc research experience | EST (GMT -5) | Time when I may be available for meetings: Weekdays: 13:00-14:00; 21:00-01:00 GMT (except Thu) Weekends: 16:00-18:00 | Weekdays (except Thu): 18:30 - 19:30, 02:30 - 06:30 Weekends: 21:30 - 23:30 | Discord, slack | https://www.linkedin.com/in/jnovikova/ | I just started a new podcast on AI - feel free to watch/listen and subscribe if interested!

## Requirement
Date Inputted | Inputted by | Requirement ID | Type of Requirement | Objective | Requirement Description | Scope (In scope/Out of scope) | Definition of Done | Tech Stack
2025-03-30 | YY | 1 |  | Develop a multi-agent system capable of dynamic resource allocation and optimisation with fairness and efficiency. | I want a system capable of autonomously managing resources so that complex allocation tasks are automated and optimised because manual management is prone to inefficiencies, biases, and human limitations. | In Scope
2025-03-30 | YY | 2 |  | Improve efficiency and reduce resource wastage through intelligent decision-making. | I want an optimised allocation mechanism so that resources are not wasted because reducing waste leads to cost savings and sustainability. | In Scope
2025-03-30 | YY | 3 |  | Enhance scalability and adaptability in response to changing conditions. | I want a system that adapts to varying loads so that it remains efficient under different operational conditions because demand fluctuations are inevitable. I want a scalable system so that it can handle different scales of operation because efficient resource distribution is necessary for both small and large-scale applications. | In Scope
2025-03-30 | YY | 4 |  | Implement real-time monitoring and decision-making capabilities. | I want real-time data processing so that the system can respond dynamically to changes because delays in decision-making can lead to inefficiencies and losses. | In Scope
2025-03-30 | YY | 5 |  | Evaluate system performance through simulations and real-world case studies. | I want a testing and simulation environment so that system behavior can be analysed before deployment because real-world implementation requires validation and risk mitigation. | In Scope

## Leave tracker
Name | Days on Leave | Comments
Jekaterina | April 4 - April 20 | I will track the updates on discord but won't be able to contribute meaningfully during this period
Gabriel | April 19 - 27 | Will have Discord and Jira on mobile
Yash | May 4-9 | I've got discord on my mobile